## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 |  | M | US:101 | Customer must login. | Customer | Group 2 | Complex | High | US:102 | Current Process Model | Functional
2 | 2 |  | M | US:102 | Customer must create account | Customer | Group 2 | Moderate | High | US:102 | Current Process Model | Technical
3 | 3 |  | C | US:103 | Customer can view Account Details | Customer | Group 2 | Easy | Low | US:101 | Current Process Model | Technical
4 | 4 |  | C | US:104 | Customer can update Account Details | Customer | Group 2 | Moderate | Medium | US:101 | Current Process Model | Technical
5 | 5 |  | C | US:105 | Customer can delete Account | Customer | Group 2 | Moderate | Medium | US:101 | Current Process Model | Technical
6 | 6 |  | C | US:106 | Customer can credit using slip | Customer | Group 2 | Moderate | High | US:101 | Current Process Model | Technical
7 | 7 |  | C | US:107 | Customer can credit using cheque | Customer | Group 2 | Moderate | High | US:101 | Current Process Model | Technical
8 | 8 |  | C | US:108 | Customer can debit using slip | Customer | Group 2 | Moderate | High | US:101 | Current Process Model | Technical
9 | 9 |  | C | US:109 | Customer can debit using cheque | Customer | Group 2 | Moderate | High | US:101 | Current Process Model | Technical
10 | 10 |  | C | US:110 | Customer can apply for loan | Customer | Group 2 | Moderate | High | US:101 | Current Process Model | Technical
11 | 11 |  | C | US:111 | Customer can check loan disbursal | Customer | Group 2 | Easy | Medium | US:101, US:110 | Current Process Model | Technical
12 | 12 |  | C | US:112 | Customer can view loan history | Customer | Group 2 | Easy | Low | US:101, US:110 | Current Process Model | Functional
13 | 13 |  | C | US:113 | Customer can view passbook | Customer | Group 2 | Easy | Low | US:101 | Current Process Model | Functional
14 | 14 |  | C | US:114 | Customer can view account statement | Customer | Group 2 | Easy | Low | US:101 | Current Process Model | Technical
22 | 22 |  | S | US:115 | Customer can log out. | Customer | Group 2 | Easy | Medium | US:101 | Current Process Model | Functional
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.
Note on A3: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Brief description of the requirements necessary to fulfill the objective
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Use column for supporting comments.
Note on Q3: Column for defining the agreed upon acceptance criteria
Note on R3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: This column is used to provide supporting information, such as changes to the original requirement.

## Sprint Backlog (Scrum 1)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
P:1 | US:101 US:102 US:103 US:104 US:105 US:106 US:107 US:108 US:109 US:110 US:111 US:112 US:113 US:114 US:115 | 1 | Module Division | All | 2020-09-21 | 2020-09-21 | 2020-09-21 | Done
|  | 1 | Create Testcases | All | 2020-09-21 | 2020-09-21 | 2020-09-21 | Done
|  | 1 | Create database details | All | 2020-09-21 | 2020-09-21 | 2020-09-21 | Done
P:2 |  | 1 | Make Class Diagrams | All | 2020-09-22 | 2020-09-22 | 2020-09-22 | Done
|  | 1 | Create a word document having all the details of project | All | 2020-09-22 | 2020-09-22 | 2020-09-22 | Done
|  | 1 | Maintain Product Backlog | All | 2020-09-22 | 2020-09-22 | 2020-09-22 | Done
|  | 1 | Maintain Sprint Backlog | All | 2020-09-22 | 2020-09-26 | 2020-09-26 | Done
P:3 |  | 1 | Create Project Structure | All | 2020-09-23 | 2020-09-23 | 2020-09-23 | Done
|  | 1 | Create Packages with proper naming conventions | All | 2020-09-23 | 2020-09-23 | 2020-09-23 | Done
|  | 1 | Create a Git repository, put all the project data there and share the link. | All | 2020-09-23 | 2020-09-23 | 2020-09-23 | Done
|  | 1 | Create mockito testcases | All | 2020-09-23 | 2020-09-24 | 2020-09-24 | Done
P:4 |  | 1 | Create Model Classes | All | 2020-09-24 | 2020-09-24 | 2020-09-24 | Done
|  | 2 | Create Repositories | All | 2020-09-24 | 2020-09-24 | 2020-09-24 | Done
P:5 |  | 1 | Create Service Classes | All | 2020-09-25 | 2020-09-25 | 2020-09-25 | Done
|  | 2 | Create Controller Classes | All | 2020-09-25 | 2020-09-25 | 2020-09-25 | Done
P:6 |  | 1 | Perform Exception Handling | All | 2020-09-26 | 2020-09-26 | 2020-09-26 | Done
|  | 2 | Perform Testing on Postman tool | All | 2020-09-26 | 2020-09-26 | 2020-09-26 | Done
|  | 3 | Add proper comments | All | 2020-09-26 | 2020-09-26 | 2020-09-26 | Done
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.

## Sprint Backlog (Scrum 2)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.